## Sprint 1
SPRINT 1 - BACKLOG
PBI ID | PBI NAME | TASK ID | TASK | ASSIGNED TO | NOT STARTED | IN PROGRESS | COMPLETED | NOTES
1 | As a customer I want to be able to register | 1.1 | Design database structure for user table | Sefira |  |  | v
|  | 1.2 | Design database structure for customer table | Sarah and Stella |  |  | v
|  | 1.3 | Create add customer query for database | Thach |  |  | v
|  | 1.4 | Design frontend web UI/UX for register page | Sarah and Stella |  |  | v
|  | 1.5 | Create logic to connect frontend and backend for customer login | Sarah |  |  | v
|  | 1.6 | User table unit testing | Sefira |  |  | v
|  | 1.7 | Customer table unit testing | Sefira |  |  | v
|  | 1.8 | Customer registration acceptance testing | Thach |  |  | v
|  | 1.9 | Customer registration system testing | Sarah |  |  | v
|  | 1.10 | Customer registation web testing | Sarah |  |  | v
2 | As a super-admin I want to be able to login | 2.1 | Frontend authorization logic | Stella |  |  | v
|  | 2.2 | Create super-admin page | Stella |  |  | v
|  | 2.3 | Create query for login with JWT | Sefira |  |  | v
|  | 2.4 | Create super-admin seeder data to add dummy data to test the database | Sefira |  |  | v
|  | 2.5 | Super-admin login acceptance testing | Sefira |  |  | v
|  | 2.6 | Super-admin login page web testing | Stella |  |  | v
3 | As an admin, I want to be able to login | 3.1 | Frontend authorization logic | Stella |  |  | v
|  | 3.2 | Create admin page | Stella |  |  | v
|  | 3.3 | Create query for login with JWT | Sefira |  |  | v
|  | 3.4 | Create admin seeder data to add dummy data to test the database | Sefira |  |  | v
|  | 3.5 | Admin login acceptance testing | Sefira |  |  | v
|  | 3.6 | Admin login page web testing | Stella |  |  | v
4 | As a customer, I want to be able to login | 4.1 | Create backend query for customer login with JWT | Sefira |  |  | v
|  | 4.2 | Create backend API for customer login | Sefira |  |  | v
|  | 4.3 | Create frontend logic to connect with login API | Sarah |  |  | v
|  | 4.4 | Create redirection page after customer logs in | Sarah |  |  | v
|  | 4.5 | Create seeder data for customer | Sefira |  |  | v
|  | 4.6 | Customer login acceptance testing | Sefira |  |  | v
|  | 4.7 | Customer login web testing | Sarah |  |  | v
5 | As a user, I want to be able to logout | 5.1 | Create logout query | Sefira |  |  | v
|  | 5.2 | Create logout API | Sefira |  |  | v
|  | 5.3 | Create logic to apply logout | Sarah |  |  | v
|  | 5.4 | Logout acceptance testing | Sefira |  |  | v
|  | 5.5 | Logout web testing | Sarah |  |  | v
6 | As a super-admin, I want to be able to create more admins | 6.1 | Create DB query to create admin | Supun |  |  | v
|  | 6.2 | Create API for create new admin | Supun |  |  | v
|  | 6.3 | Create add admin logic frontend | Stella |  |  | v
|  | 6.4 | Create the UI for adding new admin | Stella |  |  | v
|  | 6.5 | Acceptance testing | Supun |  |  | v
|  | 6.6 | Web testing | Stella |  |  | v
7 | As a customer, I want to be able to see the list of cars I can rent | 7.1 | Design location table for the database | Sefira |  |  | v
|  | 7.2 | Design car table for DB | Sefira |  |  | v
|  | 7.3 | Create query to fetch car list | Thach |  |  | v
|  | 7.4 | Create backend API to get car list | Thach |  |  | v
|  | 7.5 | Create UI/UX design to show car list | Sarah and Stella |  |  | v
|  | 7.6 | Create logic to connect frontend and backend for fetching car list | Sarah |  |  | v
|  | 7.7 | Create page to show car list | Sarah |  |  | v
|  | 7.8 | Car table unit testing | Sefira |  |  | v
|  | 7.9 | Location table unit testing | Sefira |  |  | v
|  | 7.10 | Show car list acceptance testing | Thach |  |  | v
|  | 7.11 | Show car list web testing | Sarah |  |  | v
8 | As an admin and super-admin, I want to have the ability to set a customer's account to active | 8.1 | Create change status logic | Stella |  |  | v
|  | 8.2 | Create the query | Supun |  |  | v
|  | 8.3 | Create the API | Supun |  |  | v
|  | 8.4 | Create the testing based on acceptance criteria | Supun |  |  | v

## Calculations (hidden)
This worksheet is used for the Financial Report calculations and should remain hidden.
Position
| This year | #NAME? | #NAME?
| Previous Year | #NAME? | #NAME?
| Position | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
| Key Metrics | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
All Metrics (works up to 25 metrics)
1 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
3 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
4 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
5 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
6 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
8 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
9 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
10 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
11 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
12 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
13 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
14 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
15 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
16 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
17 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
18 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
19 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
20 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
21 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
22 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
23 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
24 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
25 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!

## Sprint 2
SPRINT 2 - BACKLOG
PBI ID | PBI NAME | TASK ID | TASK | ASSIGNED TO | NOT STARTED | IN PROGRESS | COMPLETED | NOTES
9 | As an admin, I want to be able to add a new car to be rent | 9.1 | Create query method to add new car | Sefira Karina |  |  | v
|  | 9.2 | Create the API | Sefira Karina |  |  | v
|  | 9.3 | Testing based on acceptance criteria | Sefira Karina |  |  | v
|  | 9.4 | Implement add new car functionality for admin | Ignatia Stellarista |  |  | v
|  | 9.5 | Add cars for admin web testing | Ignatia Stellarista |  |  | v
11 | As an admin, I want to be able to edit existing cars | 11.1 | Create query to edit car | Sefira Karina |  |  | v
|  | 11.2 | Create the API | Sefira Karina |  |  | v
|  | 11.3 | Create testing for the edit cars query function | Sefira Karina |  |  | v
|  | 11.4 | Implement edit car functionality for admin | Ignatia Stellarista |  |  | v
|  | 11.5 | Edit cars for admin web testing | Ignatia Stellarista |  |  | v
12 | As an admin, I want to be able to delete existing cars | 12.1 | Create query function to delete cars | Sefira Karina |  |  | v
|  | 12.2 | Create the API | Sefira Karina |  |  | v
|  | 12.3 | Test the query function | Sefira Karina |  |  | v
|  | 12.4 | Implement delete car functionality for admin | Ignatia Stellarista |  |  | v
|  | 12.5 | Delete cars for admin web testing | Ignatia Stellarista |  |  | v
13 | As an admin, I want to be able to add new parking locations | 13.1 | Create query to add new locations | Supun Kwan |  |  | v
|  | 13.2 | Create the API | Supun Kwan |  |  | v
|  | 13.3 | Create testing for the add location query function | Supun Kwan |  |  | v
|  | 13.4 | Create the UI/UX interface for admin to add location | Sarah Sukamto |  |  | v
|  | 13.5 | Create the forntend connection to Google Maps API | Sarah Sukamto |  |  | v
14 | As an admin, I want to be able to delete existing locations | 14.1 | Create query function to delete locations | Supun Kwan |  |  | v
|  | 14.2 | Create the API | Supun Kwan |  |  | v
|  | 14.3 | Test the query function | Supun Kwan |  |  | v
|  | 14.4 | Create frontend connection to the delete location API | Sarah Sukamto |  |  | v
21 | As an admin, I want to be able to see the list of cars | 21.1 | Create query to see list of cars | Sefira Karina |  |  | v
|  | 21.2 | Create the API | Sefira Karina |  |  | v
|  | 21.3 | Create testing for see cars query function | Sefira Karina |  |  | v
|  | 21.4 | Display the list of cars for admin | Ignatia Stellarista |  |  | v
|  | 21.5 | List of cars for admin web testing | Ignatia Stellarista |  |  | v
22 | As an admin, I want to be able to see the list of locations | 22.1 | Create query to see locations | Thach |  |  | v
|  | 22.2 | Create the API | Thach |  |  | v
|  | 22.3 | Create testing query function | Thach |  |  | v
|  | 22.4 | Create UI/UX design to see the list of locations | Sarah Sukamto |  |  | v
|  | 22.5 | Create logic to connect frontend with backend API | Sarah Sukamto |  |  | v
23 | As a super-admin, I want to be able to see the list of admin | 23.1 | Create query to see list of admins | Sefira Karina |  |  | v
|  | 23.2 | Create the API | Sefira Karina |  |  | v
|  | 23.3 | Create testing for the see admin query function | Sefira Karina |  |  | v
|  | 23.4 | Create list of admin tab | Ignatia Stellarista |  |  | v
|  | 23.5 | List of admin tab web testing | Ignatia Stellarista |  |  | v
32 | As an admin, I want to be able to see the list of customers | 32.1 | Create query to see list of customers | Sefira Karina |  |  | v
|  | 32.2 | Create the API | Sefira Karina |  |  | v
|  | 32.3 | Create testing for the see admin query function | Ignatia Stellarista |  |  | v
|  | 32.4 | Create customer list | Ignatia Stellarista |  |  | v
|  | 32.5 | List of customer web testing | Ignatia Stellarista |  |  | v
|  | 33.1 | Create query to see locations | Thach |  |  | v
|  | 33.2 | Create the API | Thach |  |  | v
33 | As an admin, I want to be able to edit the parking locations | 33.3 | Create testing for the query function | Thach |  |  | v
|  | 33.4 | Create frontend connection to the backend API | Sarah Sukamto |  |  | v
|  | 33.5 | Create frontend connection to the Google Maps API | Sarah Sukamto |  |  | v
|  | 34.1 | Create query to see location by id | Thach |  |  | v
|  | 34.2 | Create the API | Thach |  |  | v
34 | As an admin, I want to be able to see the details of a location | 34.3 | Create testing for the query functioN | Thach |  |  | v
|  | 34.4 | Create UI/UX design to show the location details | Sarah Sukamto |  |  | v
|  | 34.5 | Create frontend connection to backend API | Sarah Sukamto |  |  | v
|  | 34.6 | Create frontend connection to Google Maps API | Sarah Sukamto |  |  | v
|  | 35.1 | Create query to see of car details by id | Sefira Karina |  |  | v
|  | 35.2 | Create the API | Sefira Karina |  |  | v
35 | As an admin, I want to be able to see details of the car | 35.3 | Create testing for the see cars query function | Sefira Karina |  |  | v
|  | 35.4 | Display the details of the car for admin | Ignatia Stellarista |  |  | v
|  | 35.5 | Display list of cars for admin web testing | Ignatia Stellarista |  |  | v
v
v
v
v
v

## Sprint 3
SPRINT 3 - BACKLOG
PBI ID | PBI NAME | TASK ID | TASK | ASSIGNED TO | NOT STARTED | IN PROGRESS | COMPLETED | NOTES
10 | As a customer, I want to be able to see the details of my account | 10.1 | Create query to see details of customer's account | Sefira |  |  | v
|  | 10.2 | Create the API | Sefira |  |  | v
|  | 10.3 | Create the test for the query | Sefira |  |  | v
|  | 10.4 | Create frontend UI/UX | Sarah and Stella |  |  | v
|  | 10.5 | Create connection from frontend to backend | Sarah and Stella |  |  | v
|  | 10.6 | Create web testing | Sarah and Stella |  |  | v
15 | As a customer, I want to be able to lodge a booking | 15.1 | Design the DB table for booking | Sefira |  |  | v
|  | 15.2 | Create query to make booking | Sefira |  |  | v
|  | 15.3 | Create the API | Sefira |  |  | v
|  | 15.4 | Create the test for the query | Sefira |  |  | v
|  | 15.5 | Create frontend UI/UX | Sarah and Stella |  |  | v
|  | 15.6 | Create connection from frontend to backend | Sarah and Stella |  |  | v
|  | 15.7 | Create web testing | Sarah and Stella |  |  | v
16 | As a customer, I want to be able to see my ongoing booking | 16.1 | Create query to see booking | Supun |  |  | v
|  | 16.2 | Create the API | Supun |  |  | v
|  | 16.3 | Create the test for the query | Supun |  |  | v
|  | 16.4 | Create frontend UI/UX | Sarah and Stella |  |  | v
|  | 16.5 | Create connection from frontend to backend | Sarah and Stella |  |  | v
|  | 16.6 | Create web testing | Sarah and Stella |  |  | v
20 | As a customer, I want to be able to edit the return date and location of my ongoing booking | 20.1 | Create the query | Sefira |  |  | v
|  | 20.2 | Create the API | Sefira |  |  | v
|  | 20.3 | Create the test for the query | Sefira |  |  | v
|  | 20.4 | Create frontend UI/UX | Sarah and Stella |  |  | v
|  | 20.5 | Create connection from frontend to backend | Sarah and Stella |  |  | v
|  | 20.6 | Create web testing | Sarah and Stella |  |  | v
25 | As a customer, I want to be able to see the cars' available rent dates | 25.1 | Create the query | Thach |  |  | v
|  | 25.2 | Create the API | Thach |  |  | v
|  | 25.3 | Create the test for the query | Thach |  |  | v
|  | 25.4 | Create frontend UI/UX | Sarah and Stella |  |  | v
|  | 25.5 | Create connection from frontend to backend | Sarah and Stella |  |  | v
|  | 25.6 | Create web testing | Sarah and Stella |  |  | v
36 | As an admin, I want to be able to see customer's bookings | 36.1 | Create the query to see customer's bookings | Thach |  |  | v
|  | 36.2 | Create the API | Thach |  |  | v
|  | 36.3 | Create the test for the query | Thach |  |  | v
|  | 36.4 | Create frontend UI/UX | Sarah and Stella |  |  | v
|  | 36.5 | Create connection from frontend to backend | Sarah and Stella |  |  | v
|  | 36.6 | Create web testing | Sarah and Stella |  |  | v
37 | As a customer, I want to be able to delete my booking | 37.1 | Create the query to delete booking | Supun |  |  | v
|  | 37.2 | Create the API | Supun |  |  | v
|  | 37.3 | Create the test for the query | Supun |  |  | v
|  | 37.4 | Create frontend UI/UX | Sarah and Stella |  |  | v
|  | 37.5 | Create connection from frontend to backend | Sarah and Stella |  |  | v
|  | 37.6 | Create web testing | Sarah and Stella |  |  | v
38 | As a user, I want to activate my booking | 38.1 | Create the query to activate booking | Thach |  |  | v
|  | 38.2 | Create the API | Thach |  |  | v
|  | 38.3 | Create the test for the query | Thach |  |  | v
|  | 38.4 | Create frontend UI/UX | Sarah and Stella |  |  | v
|  | 38.5 | Create connection from frontend to backend | Sarah and Stella |  |  | v
|  | 38.6 | Create web testing | Sarah and Stella |  |  | v
39 | As an admin, I want to see details of a booking | 39.1 | Create the query to see booking details | Thach |  |  | v
|  | 39.2 | Create the API | Thach |  |  | v
|  | 39.3 | Create the test for the query | Thach |  |  | v
|  | 39.4 | Create frontend UI/UX | Sarah and Stella |  |  | v
|  | 39.5 | Create connection from frontend to backend | Sarah and Stella |  |  | v
|  | 39.6 | Create web testing | Sarah and Stella |  |  | v

## Sprint 4
SPRINT 4 - BACKLOG
PBI ID | PBI NAME | TASK ID | TASK | ASSIGNED TO | NOT STARTED | IN PROGRESS | COMPLETED | NOTES
17 | As a customer, I want to be able to see my booking history | 17.1 | Design & create migration for the history table | Sefira |  |  | v
|  | 17.2 | Create the query | Supun |  |  | v
|  | 17.3 | Create the API | Supun |  |  | v
|  | 17.4 | Create the test script | Supun |  |  | v
|  | 17.5 | Create the UI/UX | Sarah and Stella |  |  | v
|  | 17.6 | Create the connection from frontend to backend | Sarah and Stella |  |  | v
|  | 17.7 | Create web testing | Sarah and Stella |  |  | v
24 | As a super-admin, I want to be able to delete existing admin | 24.1 | Create the query | Thach |  |  | v
|  | 24.2 | Create the API | Thach |  |  | v
|  | 24.3 | Create the test script | Thach |  |  | v
|  | 24.4 | Create the UI/UX | Sarah and Stella |  |  | v
|  | 24.5 | Create the connection from frontend to backend | Sarah and Stella |  |  | v
|  | 24.6 | Create web testing | Sarah and Stella |  |  | v
26 | As user, I want to be able to reset my password | 26.1 | Create the query | Supun |  |  | v
|  | 26.2 | Create the API | Supun |  |  | v
|  | 26.3 | Create the test script | Supun |  |  | v
|  | 26.4 | Create the UI/UX | Sarah and Stella |  |  | v
|  | 26.5 | Create the connection from frontend to backend | Sarah and Stella |  |  | v
|  | 26.6 | Create web testing | Sarah and Stella |  |  | v
28 | As a customer, I want to be able to edit my profile information | 28.1 | Create the query | Thach |  |  | v
|  | 28.2 | Create the API | Thach |  |  | v
|  | 28.3 | Create the test script | Thach |  |  | v
|  | 28.4 | Create the UI/UX | Sarah and Stella |  |  | v
|  | 28.5 | Create the connection from frontend to backend | Sarah and Stella |  |  | v
|  | 28.6 | Create web testing | Sarah and Stella |  |  | v
29 | As a customer, I want to be able to see my card activation status | 29.1 | Create the UI/UX | Sarah and Stella |  |  | v
|  | 29.2 | Create the connection from frontend to backend | Sarah and Stella |  |  | v
|  | 29.3 | Create web testing | Sarah and Stella |  |  | v
31 | As a customer, I want to be able to complete my returning step | 31.1 | Create the query | Sefira |  |  | v
|  | 31.2 | Create the API | Sefira |  |  | v
|  | 31.3 | Create the test script | Sefira |  |  | v
|  | 31.4 | Create the UI/UX | Sarah and Stella |  |  | v
|  | 31.5 | Create the connection from frontend to backend | Sarah and Stella |  |  | v
|  | 31.6 | Create web testing | Sarah and Stella |  |  | v
40 | As an admin, I want to see all customer's booking histories | 40.1 | Create the query | Thach |  |  | v
|  | 40.2 | Create the API | Thach |  |  | v
|  | 40.3 | Create the test script | Thach |  |  | v
|  | 40.4 | Create the UI/UX | Sarah and Stella |  |  | v
|  | 40.5 | Create the connection from frontend to backend | Sarah and Stella |  |  | v
|  | 40.6 | Create web testing | Sarah and Stella |  |  | v
41 | As a user I want to be able to complete the payment | 41.1 | Install paypal dependencies via composer | Sefira |  |  | v
|  | 41.2 | Make function to create payment | Sefira |  |  | v
|  | 41.3 | Make function to show payment execution result | Sefira |  |  | v
|  | 41.4 | Create the APIs | Sefira |  |  | v
|  | 41.5 | Create the UI/UX | Sarah and Stella |  |  | v
|  | 41.6 | Create the connection from frontend to backend | Sarah and Stella |  |  | v
|  | 41.7 | Create web testing | Sarah and Stella |  |  | v